## Master Plan
Retro Game Platform Production Plan Through May 10, 2026 | Retro Game Platform Production Plan Through May 10, 2026 | Retro Game Platform Production Plan Through May 10, 2026 | Retro Game Platform Production Plan Through May 10, 2026 | Retro Game Platform Production Plan Through May 10, 2026 | Retro Game Platform Production Plan Through May 10, 2026 | Retro Game Platform Production Plan Through May 10, 2026 |  | Launch Snapshot | Launch Snapshot | Launch Snapshot | Launch Snapshot
Retro Game Platform Production Plan Through May 10, 2026 | Retro Game Platform Production Plan Through May 10, 2026 | Retro Game Platform Production Plan Through May 10, 2026 | Retro Game Platform Production Plan Through May 10, 2026 | Retro Game Platform Production Plan Through May 10, 2026 | Retro Game Platform Production Plan Through May 10, 2026 | Retro Game Platform Production Plan Through May 10, 2026 |  | Metric | Value | Target | Notes
This sheet is the working master list. Keep the Status, Owner, and Notes columns up to date daily. The most urgent production blockers are Bonum payments, custom-game security, CI/lint, and staging readiness. | [7 empty] | Days until launch | 16 | 0 | Measured from April 24, 2026
[8 empty] | P0 items | 15 | 0 | Critical blockers
[8 empty] | P1 items | 7 | 0 | Important but secondary
Priority | Area | Task | Why It Matters | Status | Deadline | Notes | Owner | P2 items | 2 | 0 | Polish and operations
P0 | Payments | Replace simulated payments with Bonum payment integration | Current backend payment flow is demo-only | Not started | 2026-05-01 | Use Bonum Gateway as the production provider |  | Status | Count
P0 | Payments | Add Bonum webhook or callback handling for payment success/failure | Prevents fake client-side payment success | Not started | 2026-05-01 | Subscription state must be confirmed from Bonum server callbacks |  | Not started | 14
P0 | Payments | Test monthly and yearly subscription flows end-to-end through Bonum | Revenue path must work before launch | Not started | 2026-05-02 | Include failed payment and retry cases |  | Partial | 8
P0 | Security | Implement CSP for community games | Listed as future enhancement and now required | Not started | 2026-04-29 | Needed for untrusted game content |  | Done | 0
P0 | Security | Lock down iframe sandbox and parent messaging rules | Reduces iframe escape and unsafe communication | Partial | 2026-04-29 | Define an explicit postMessage allowlist
P0 | Security | Add server-side rate limiting | Reduces abuse on auth, submissions, payments, and rooms | Not started | 2026-04-30 | Apply per route group
P0 | Marketplace | Verify submission scan blocks dangerous patterns | Core marketplace protection | Partial | 2026-04-30 | Test with known bad payloads
P0 | Marketplace | Validate submission review workflow end-to-end | Admin approval path must be reliable | Partial | 2026-05-01 | Submit, reject, approve, and disable in staging
P0 | Admin | Verify admin-only permissions everywhere | Prevents privilege escalation | Not started | 2026-05-01 | Review route protection and client visibility
P0 | Quality | Set up ESLint so npm run lint works non-interactively | CI and release gating depend on it | Not started | 2026-04-27 | Current command opens setup prompt
P0 | Quality | Add CI pipeline for build, lint, and tests | Prevents broken deploys | Not started | 2026-04-28 | GitHub Actions is enough
P0 | Quality | Add smoke tests for auth, rooms, matchmaking, chess, submissions, and admin | Minimum confidence for launch | Not started | 2026-05-02 | Focus on high-risk flows first
P0 | Ops | Set up production and staging envs for frontend, backend, DB, and Redis | Needed for safe launch rehearsal | Partial | 2026-04-28 | Vercel plus Railway/Render plus Upstash is fine
P0 | Ops | Centralize secrets and rotate any exposed local test creds | Secret hygiene before production | Partial | 2026-04-28 | Move secrets into managed envs
P0 | Ops | Add monitoring and error logging | You need visibility on launch day | Not started | 2026-05-02 | Sentry plus uptime checks is enough
P1 | Database | Verify migrations are production-safe and reproducible | Avoids schema drift on deploy | Partial | 2026-05-02 | Check Prisma migration history carefully
P1 | Reliability | Add backup and restore plan for Postgres | Prevents irreversible launch-day data loss | Not started | 2026-05-03 | Test at least one restore
P1 | Reliability | Add stronger readiness checks | Improves deploy confidence | Partial | 2026-05-03 | Health exists, readiness needs more depth
P1 | Frontend | Confirm production API and WebSocket config works | Prevents frontend/backend connection failures | Partial | 2026-05-03 | Test deployed URLs, not localhost assumptions
P1 | Multiplayer | Run multiplayer soak test with several users | Checks socket stability before launch | Not started | 2026-05-05 | Aim for a 30 to 60 minute session
P1 | Marketplace | Moderate and verify sample community games manually | Catches content and policy gaps | Not started | 2026-05-05 | Use the staging admin flow
P1 | Admin | Add audit visibility for approvals, rejections, and payments | Helps moderation and debugging | Partial | 2026-05-05 | Simple logs are acceptable for v1
P2 | Docs | Create launch runbook and rollback plan | Needed if deploy goes wrong | Not started | 2026-05-07 | Keep it short and operational
P2 | Docs | Create support checklist for the first 48 hours | Improves triage speed after launch | Not started | 2026-05-08 | Capture likely failure paths

## Schedule
Daily Schedule To Production Launch | Daily Schedule To Production Launch | Daily Schedule To Production Launch | Daily Schedule To Production Launch
Daily Schedule To Production Launch | Daily Schedule To Production Launch | Daily Schedule To Production Launch | Daily Schedule To Production Launch
Date | Must Be Done By End Of Day | Priority | Status
2026-04-24 | Finalize launch scope, assign owners, confirm Bonum as payment provider | Critical | Not started
2026-04-25 | Start Bonum integration discovery, set up ESLint, create CI skeleton | Critical | Not started
2026-04-26 | Implement basic Bonum payment backend and create staging env | Critical | Not started
2026-04-27 | Lint working, CI running, Bonum checkout flow sketched | Critical | Not started
2026-04-28 | Secrets cleaned up and Bonum env variables finalized | Critical | Not started
2026-04-29 | CSP and iframe/message hardening implemented while Bonum callback flow is integrated | Critical | Not started
2026-04-30 | Rate limiting and marketplace scan verification complete | Critical | Not started
2026-05-01 | Bonum payment integration complete and admin permissions validated end-to-end | Critical | Not started
2026-05-02 | Smoke tests added for core flows, Bonum payment flow tested, monitoring/logging live | Critical | Not started
2026-05-03 | DB migration check and backup/restore rehearsal complete | Critical | Not started
2026-05-04 | Frontend/backend production config verified in staging | High | Not started
2026-05-05 | Multiplayer soak test and moderation tests completed | High | Not started
2026-05-06 | Fix highest-severity bugs only | High | Not started
2026-05-07 | Code freeze except launch blockers, runbook and rollback ready | High | Not started
2026-05-08 | Full staging rehearsal from signup to payment to gameplay to admin review | Critical | Not started
2026-05-09 | Final regression and launch signoff | Critical | Not started
2026-05-10 | Production launch with monitoring and active bug triage | Critical | Not started

## Readiness
Launch Readiness Checklist | Launch Readiness Checklist | Launch Readiness Checklist | Launch Readiness Checklist | Launch Readiness Checklist
Launch Readiness Checklist | Launch Readiness Checklist | Launch Readiness Checklist | Launch Readiness Checklist | Launch Readiness Checklist
Category | Check | Pass / Fail | Owner | Notes
Payments | Real card payment works in production
Payments | Subscription updates from webhook correctly
Payments | Failed payment path handled safely
Auth | Login and session flow works in production
Auth | Role-based access enforced for developer/admin actions
Marketplace | Submission scan rejects unsafe files and patterns
Marketplace | Approved games appear correctly in community listings
Marketplace | Rejected and disabled games are hidden correctly
Security | CSP active for community game content
Security | iframe sandbox verified
Security | postMessage contract restricted
Security | Rate limiting enabled on sensitive routes
Multiplayer | Room create, join, and start flow works
Multiplayer | Matchmaking works with multiple clients
Multiplayer | Chess gameplay finishes without desync
Ops | Frontend deploy works
Ops | Backend deploy works
Ops | Database migrations apply cleanly
Ops | Redis connection works in production
Ops | Monitoring and alerts are working
Ops | Backup and restore tested
Quality | CI passes on main branch
Quality | Lint passes
Quality | Smoke tests pass
Release | Rollback plan documented
Release | Launch-day owner assignments confirmed

## Risks
Launch Risk Register | Launch Risk Register | Launch Risk Register | Launch Risk Register | Launch Risk Register
Launch Risk Register | Launch Risk Register | Launch Risk Register | Launch Risk Register | Launch Risk Register
Risk | Impact | Likelihood | Mitigation | Decision Date
Payment integration slips | Launch blocked or revenue broken | High | Choose provider immediately and cut extras | 2026-04-24
Marketplace security gap | Abuse or malicious content reaches production | High | Prioritize CSP, sandboxing, scan verification, and moderation | 2026-04-24
No automated tests | Late regressions before launch | High | Add smoke tests first instead of broad deep coverage | 2026-04-25
No working lint and CI gate | Broken code reaches production | High | Configure ESLint and CI this week | 2026-04-27
Deployment misconfiguration | Production outage on launch | Medium | Run a staging rehearsal and keep a rollback plan | 2026-05-07
Socket instability under load | Multiplayer failure at launch | Medium | Run a soak test before code freeze | 2026-05-05
Secrets and env mismanagement | Auth or payment outage or exposure | Medium | Centralize and rotate secrets | 2026-04-28